## Sheet1
Task Name | Start | End | Duration (days)
CSV filter input and output files (K) | 2016-09-18 | 2016-09-25 | 7
Read in CSV and serial port to excel (J) | 2016-09-18 | 2016-09-25 | 7
Read in voltage -> output to serial port (A) | 2016-09-18 | 2016-09-25 | 7
Catch up/Find contribution (W) | 2016-09-18 | 2016-09-25 | 7
Interfacing input/output for audio/visual (K) | 2016-09-25 | 2016-10-02 | 7
Testing graphing/interfacing (J) | 2016-09-25 | 2016-10-02 | 7
Serial port -> ADC and DMA (A) | 2016-09-25 | 2016-10-02 | 7
Test frequency/Vrms conversions (W) | 2016-09-25 | 2016-10-02 | 7
Pulse Width Module (K) | 2016-10-02 | 2016-10-09 | 7
Live testing graphing -> debug/test (J) | 2016-10-02 | 2016-10-09 | 7
Test ADC and DMA live V/Freq (A) | 2016-10-02 | 2016-10-09 | 7
Pulse Width Module interface (W) | 2016-10-02 | 2016-10-09 | 7
Prep for Major Design Review (Team) | 2016-10-09 | 2016-10-13 | 4
MDR - Design Schematics (K) | 2016-10-09 | 2016-10-13 | 4
MDR - Implementation (J) | 2016-10-09 | 2016-10-13 | 4
MDR - Demo (A) | 2016-10-09 | 2016-10-13 | 4
Major Design Reviews | 2016-10-13 | 2016-10-13 | 1
PWM work (W) | 2016-10-09 | 2016-10-16 | 7
Written Progress Report | 2016-10-16 | 2016-10-16 | 1
Test/Debug - Graphing -> Test | 2016-10-16 | 2016-10-23 | 7
Test/Debug - PWM -> Test | 2016-10-16 | 2016-10-23 | 7
Test/Debug - DMA -> Debug | 2016-10-16 | 2016-10-23 | 7
Test/Debug - Input/Output PWM -> Test/Debug | 2016-10-16 | 2016-10-23 | 7
Prep for Closed Beta Prototype | 2016-10-23 | 2016-10-30 | 7
Test/Debug | 2016-10-23 | 2016-10-30 | 7
Fix/Improve on demo | 2016-10-23 | 2016-10-30 | 7
Finalize Closed Beta Prototype | 2016-10-30 | 2016-11-06 | 7
Test/Debug | 2016-10-30 | 2016-11-06 | 7
Implement graph/light | 2016-10-30 | 2016-11-06 | 7
Finalize Closed Beta Presentation | 2016-11-06 | 2016-11-10 | 4
Closed Beta Prototype | 2016-11-10 | 2016-11-10 | 1
Fix suggetions/problems from Closed Beta | 2016-11-10 | 2016-11-13 | 3
Finalize Beta Prototype | 2016-11-13 | 2016-11-20 | 7
Poster - Title and Abstract | 2016-11-16 | 2016-11-16 | 1
Additions? | 2016-11-13 | 2016-11-20 | 7
Thanksgiving Break | 2016-11-20 | 2016-11-27 | 7
Work on Poster | 2016-11-27 | 2016-12-04 | 7
Work on Final Report | 2016-11-27 | 2016-12-04 | 7
Continue Test/Debug -> Finalize Presentation | 2016-11-27 | 2016-12-09 | 12
Print Poster | 2016-12-06 | 2016-12-06 | 1
Formal Presentation | 2016-12-09 | 2016-12-09 | 1
Final Report | 2016-12-11 | 2016-12-11 | 1